## Team WIP Tracker
SuA Glow — Team Work in Progress & Operating Standards
Review open team issues, assign accountability, document decisions, and retain the final operating standard.
# | Area | Topic | Type | Status/Issue / Policy Standard | Action / Decision Needed | Key Person Assigned | Priority | Status | Date Opened | Date Resolved | Resolution / Final Standard / Notes
1 | Dev | Website Update | Status | Complete & in Development Sandbox: K-Beauty Facials > LDM Water DropLifting, Salmon PN, Collagen, and Tone Up. To Do: Hydration & Glow Draft Submitted: Korean Scalp & Hair Restoration | Push out completed K-Beauty Facials approved: Tone Up. Begin design and development of Korean scalp & hair rejuvenation. | Marcus | High
2 | Dev | Website Update | Status | 1.IG to homepage app execution. 2. Google Calendar configuration 3. Google campaign | Complete IG and assess Google calendar. | Marcus | High
3 | Strategy/ Marketing | Membership | Status | Completed draft of membership | Review with Sophia & Jasmine | Kameron | High
4 | Strategy/ Marketing | P/L | Status | Finalizing executive summary | Review with Sophia | Kameron | High
5 | Provider | Monthly Promo | Status | Need 3 promos for September | Sophia to create | Sophia | High
6 | Operations | Procedure Timing | Policy | Appointment times need to adequately cover patient prep, pre/post photos, treatment, initial charting, cleanup, and room turnover. | *Update online booking times. *Reschedule patients that just show up and add a bonus for re-scheduling. *Establish standard appointment duration by procedure/service. | Jasmine | High | Open | 2026-08-25 | 2026-08-31
7 | Operations | All Patients on Schedule | Policy | *Every patient encounter must appear on the schedule, including consultations, treatments, follow-ups, touch-ups, models, complimentary services, and add-ons. * No treatment will be allowed without patient medical history and government form of ID' | Reinforce expectation and ensure consistent scheduling workflow. | Jasmine | High | Open
8 | Operations | Late Hours / Closing Time | WIP | *Determine which days SuA Glow should offer later appointments and how long the clinic should remain open when no patients are scheduled. * Confirm how calls are handled during business hours. | Establish late-clinic days, last appointment times, and closing rules. | Jasmine | High | Open
9 | Provider | New Patient Prescriptions | Policy | No prescriptions for new patients on the same day of their initial service. | Incorporate into patient/provider workflow and communicate to clinical team. |  | High | Open
10 | Operations | Post-Procedure Photos | Policy | Post-procedure photos must be taken when required by the treatment protocol and documented in the patient record. | Standardize responsibility, timing, and documentation. |  | High | Open
11 | Operations | No-Show Patient Follow-Up | WIP → Policy | Every no-show should receive timely outreach with an attempt to reschedule. No-shows should not simply remain unresolved on the schedule. | Establish same-day outreach, second follow-up timing, number of attempts, owner, and documentation requirements. |  | High | Open
12 | Operations | Cancellation Follow-Up | WIP → Policy | Patients who cancel without rebooking should be actively followed up with. | Establish follow-up cadence and responsibility for rebooking. |  | High | Open
13 | Operations | Consultation Follow-Up | WIP | Patients who complete a consultation but do not schedule treatment represent an important follow-up opportunity. | Establish follow-up process and track consultation-to-treatment conversion. |  | High | Open
14 | Operations | Treatment Plan Follow-Up | WIP | Patients who begin a recommended treatment series or plan should not inadvertently fall out of care. | Identify patients overdue for their next recommended treatment and establish outreach. |  | Medium | Open
15 | Operations | Late Patients | WIP | Late arrivals can affect treatment quality and subsequent appointments.Patients are allowed a 15 minulate delay. After 30 minutes, patients must be re-scheduled. | Establish grace periods and criteria for shortening or rescheduling appointments. |  | Medium | Open
16 | Operations | Chart Completion | Policy | Treatment documentation, required photos, products/devices used, and applicable treatment details should be completed consistently and promptly. | Establish same-day/end-of-day completion expectations. |  | High | Open
17 | Operations | Schedule & Room Utilization | WIP | Appointment sequencing should minimize unnecessary gaps while providing appropriate treatment and turnover time. | Review scheduling templates and provider/room utilization. |  | Medium | Open
18 | Provider | Weekly Schedule Review | Operating Rhythm | Upcoming appointments should be reviewed proactively for long procedures, staffing requirements, open capacity, patient follow-ups, and potential conflicts. | Establish weekly review time and owner. |  | Medium | Open

## Tracker Guide
Tracker Guide & Status Definitions
Status | Definition
Open | Issue has been identified but work has not yet started.
In Progress | Assigned person is actively working the item.
Pending Decision | Work or analysis is complete enough that a management/team decision is required.
Resolved | Decision has been implemented and the final standard is documented.
Field | How to Use It
Key Person Assigned | One person accountable for driving the item to resolution, even if others contribute.
Date Opened | Date the issue or policy item was formally added to the tracker.
Date Resolved | Date the agreed standard was implemented—not merely discussed.
Resolution / Final Standard | Document the final decision or operating rule so the history is retained after resolution.